## Build
Document Legenda
Document type | Template
Document version | 0.2
Explanation
Story |  | (aka Product Backlog Item, Work Item) A story is an individual feature or requirement that the business wants. It is something that is deliverable (i.e. production ready) within a single sprint. A story should use the INVEST acronym. However, it was also thought that a story is only a starting point for a discussion; it does not have all the information the team may need to complete the job. Stories are often written in a specific format: * As a [end user of the required feature] * I want [actual thing the user wants to be able to do once the feature is live] * So that [why they want this feature / the benefit this feature brings] Although this format has caught on and is commonplace, it is not the only approach. One team stressed that they alter the above format to put the “So that …” first. I think this is a smart idea as everything should be done for a valid business reason: starting with explaining the benefit certainly makes sense to me. An example story: “As a customer, I want to be able to save a product in my wishlist so that I can view it again later.”
Epic |  | An epic is a big story. A requirement that is just too big to deliver in a single sprint. Epics need to be broken into smaller deliverables (stories). This helps them support the agile principles (e.g. delivering working software frequently, early continuous delivery, regular reflection). An example epic: “As a customer, I want to be able to have wishlists so that I can come back to buy products later.”
Themes |  | A collection of stories by category. A basket or bucket of stories. By its nature, an epic can also be a theme in itself. However, interestingly, one group thought that themes should refer to business goals. My view is that everything should have a goal (otherwise why are you doing it?!) An example theme: “Wishlist”.
Tasks |  | The elements of a story. Stepping stones to take the story to ‘Done’. Tasks often follow the SMART acronym: specific, measurable, achievable, relevant, time-boxed (although what the letters stand for seems to be hotly debated). However, many teams don’t break their stories down into tasks. I have found that splitting stories into tasks encourages teams to split work horizontally, whereas we try to slice work vertically. An example task: “Put ‘Add to wishlist’ button on each product page.”

## Acronyms
Invest | It’s a tidy acronym: I – Independent The story should be independent from other stories so that, should something block this story, the other items in the iteration are not affected (domino effect). Obviously this is sometimes difficult, but the more independent each story is, the better. N – Negotiable The iron triangle (quality, scope, time and resources) sometimes needs to be broken and the business needs to be prepared to negotiate on what gives. V – Business Value If it doesn’t have value to the business, why the hell are you doing it?! E – Estimate There must be sufficient information available to allow the team to estimate the story. S – Size The story should be a good size (i.e. not an epic) to allow the team to be able to complete it within an iteration. The difference between estimate and size was often confused: A user story may have sufficient information to allow it to be sized, but it could be a 100-point story. That is estimate-able but is not a good size. A user story might be 2 points, but not contain enough information for the team to give it a size. That is a good size but is not estimate-able (obviously the team won’t know that it’s a 2-point story though) T – Testable If you’ve got acceptance criteria / Conditions of Satisfaction, then you should be able to test it (note: this is not how to test the story, but what means the story passes). Did you know? User stories aren’t an original Scrum concept; they originate from Extreme Programming. However, most Scrum teams and theoreticians have binned the old Scrum practice of Product Backlog Items (or PBIs) and favour user stories.

## Theme
Themes
| Category | Story

## Epic
As a | <who> | I want | <what> | So that | <why>

## Features
As a | <who> | I want | <what> | So that | <why>

## Story
As a | <who> | I want | <what> | So that | <why>

## Task
Daily Scrum | Date:
Task Prio | Task nr | Description | Story Points | Esitimated Hours | Developer | To Do | In Progress | Done | Impediment | Actual Time
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25